## How-To
DMAIC PROJECT FILES
A linked set of the core DMAIC project documents: charter, data collection plan, control plan and tollgate checklist, plus a live dashboard.
Purpose
A DMAIC project generates standing documents that are referenced throughout the project and reviewed at every phase gate. This workbook keeps them together in one linked file instead of scattered across separate documents, and the Dashboard rolls up gate completion automatically.
Workflow: What to Complete, and When
Tab | What It Covers | When to Complete | Typical Owner
Project Charter | Problem, goal, success metrics, scope, milestones, team and approvals. Anchors the whole project. | Define (complete first) | Project Lead, Sponsor
Data Collection Plan | Every metric with its operational definition, data type, collection method and sampling plan. | Measure, before collecting data | Project Lead, data owners
Control Plan | How each process characteristic is monitored and what happens when it drifts. | Control, once the process is stable | Process Owner
Tollgate Checklist | Gate criteria for every phase, with status, approver, date and evidence. | End of every phase | Project Lead, Sponsor
Dashboard | Live rollup of gate completion and open items. Read-only: nothing is typed here. | Any time | Everyone
DMAIC at a Glance
Phase | Key Question | Main Deliverable Here | Gate Progress
Define | What problem are we solving, for whom, and by when? | Project Charter | 0%
Measure | How is the process performing today? | Data Collection Plan | 0%
Analyze | What is causing the gap? | Root-cause evidence | 0%
Improve | What solution closes the gap, and does it work? | Pilot results | 0%
Control | How do we hold the gains? | Control Plan | 0%
Working Conventions
Input cell | Blue-shaded cells are for you to complete. Dates, percentages, statuses and lists are validated.
Calculated cell | White cells with formulas or links. Do not overwrite them; they feed the Dashboard.
Complete | Gate criterion finished and approved.
In Progress | Work is underway but the criterion is not yet met.
Not Started | Default status. The Dashboard counts only these three statuses.
Adding rows | Tables grow automatically: type in the first empty row beneath a table. IDs fill in on their own.
Example rows | Italic rows in the Data Collection Plan and Control Plan are samples. Overwrite them.
Template version 4.0 ¦ Last updated: 2026-10-06

## Project Charter
DMAIC PROJECT CHARTER |  |  | ◄ How-To
Complete this tab first. It anchors the problem, goal, scope and team for the whole project. Blue-shaded cells are inputs; white cells calculate automatically, and the Dashboard reads its project details from here.
Project Details
Project Name
Project Lead |  | Sponsor
Process Owner |  | Coach / Mentor
Start Date |  | Target Completion
Planned Duration (days) |  | Days to Target
Problem Statement
What is wrong, where, how big, and since when? State the gap in facts and numbers. No causes, no solutions.
Goal Statement (SMART)
Specific, Measurable, Achievable, Relevant, Time-bound. Example: Reduce order cycle time from 52 to 36 hours by Mar 31.
Business Case
Why does this matter? Quantify the impact on cost, revenue, customers or risk, and the cost of doing nothing.
Success Metrics
Metric | Baseline | Target | Unit of Measure
Primary (Y):
Secondary:
Guardrail:
In Scope / Out of Scope
In Scope |  | Out of Scope
Project Milestones
Phase | Planned Start | Planned End | Actual End
Define
Measure
Analyze
Improve
Control
Team Roster
Name | Role | Department | % Time Allocated
Approvals
Role | Name | Signature | Approval Date
Sponsor
Process Owner
Project Lead

## Data Collection Plan
DATA COLLECTION PLAN | [7 empty] | ◄ How-To
Complete during Measure, before data collection starts, so every metric has an agreed operational definition and sampling approach. Italic rows are examples: overwrite them with your own.
ID | Measure / Metric | Measure Type | Operational Definition | Data Type | Collection Method | Sample Size / Frequency | Who Collects | Where / When
DC-01 | Order cycle time | Output (Y) | Elapsed hours from order receipt to shipment confirmation | Continuous | Automatic timestamp export from ERP | All orders, 4 weeks | Systems analyst | ERP order log, daily export
DC-02 | Defect occurrence | Output (Y) | Unit meets the visual and dimensional spec sheet at final inspection | Discrete (Pass/Fail) | Visual check at final inspection station | 100% of units, 2 weeks | Final inspector | Final inspection station, each shift

## Control Plan
CONTROL PLAN | [6 empty] | ◄ How-To
Complete during Control, once the improved process is stable, to document how the gains will be sustained. The italic row is an example: overwrite it with your own.
ID | Process Step | Product / Process Characteristic | Specification / Tolerance | Control Method | Sample Size / Frequency | Reaction Plan | Owner
CP-01 | Final inspection | Label placement offset | +/- 2mm from spec drawing | Vision system, automatic reject | 100% | Quarantine unit, notify line lead, log in nonconformance tracker

## Tollgate Checklist
TOLLGATE CHECKLIST |  |  |  |  | ◄ How-To
Update at the end of each DMAIC phase. Set each criterion to Not Started, In Progress or Complete; the Dashboard rolls the results up automatically. Record the approver, approval date and where the evidence lives.
Phase | Gate Criteria | Status | Approver | Approval Date | Evidence / Notes
Define | Project charter is complete and signed off by the sponsor | Not Started
Define | Process scope (SIPOC) and customer CTQs are documented | Not Started
Define | Stakeholder analysis and communication plan are complete | Not Started
Measure | Data collection plan is complete with operational definitions | Not Started
Measure | Measurement system has been validated (Gage R&R or equivalent) | Not Started
Measure | Baseline process performance is established | Not Started
Analyze | Potential root causes have been identified (fishbone, C&E matrix) | Not Started
Analyze | Root causes have been statistically or practically verified | Not Started
Improve | Solutions have been generated and screened | Not Started
Improve | Selected solution has been piloted with measured results | Not Started
Control | Control plan is documented and in place | Not Started
Control | Process has been handed off to the process owner | Not Started

## Dashboard
DMAIC PROJECT DASHBOARD |  |  |  |  | ◄ How-To
Live rollup of the Tollgate Checklist and Project Charter. Nothing on this tab is entered by hand: update the source tabs and this page refreshes.
Project Snapshot |  | Tollgate Progress
Project | Not entered | % Complete | Complete | In Progress | Not Started
Project Lead | Not entered | 0% | 0 | 0 | 12
Sponsor | Not entered
Timeline | Not set
Days to Target | Not set | of 12 criteria | 0% of total | 0% of total | 100% of total
Current Phase | Define
Progress by Phase
Phase | Progress | Complete | In Progress | Not Started | Total
Define | 0% | 0 | 0 | 3 | 3
Measure | 0% | 0 | 0 | 3 | 3
Analyze | 0% | 0 | 0 | 2 | 2
Improve | 0% | 0 | 0 | 2 | 2
Control | 0% | 0 | 0 | 2 | 2
Overall | 0% | 0 | 0 | 12 | 12
Status by Phase
Open Gate Criteria (12)
Phase | Gate Criteria | Status | Approver
Define | Project charter is complete and signed off by the sponsor | Not Started | —
Define | Process scope (SIPOC) and customer CTQs are documented | Not Started | —
Define | Stakeholder analysis and communication plan are complete | Not Started | —
Measure | Data collection plan is complete with operational definitions | Not Started | —
Measure | Measurement system has been validated (Gage R&R or equivalent) | Not Started | —
Measure | Baseline process performance is established | Not Started | —
Analyze | Potential root causes have been identified (fishbone, C&E matrix) | Not Started | —
Analyze | Root causes have been statistically or practically verified | Not Started | —
Improve | Solutions have been generated and screened | Not Started | —
Improve | Selected solution has been piloted with measured results | Not Started | —
Control | Control plan is documented and in place | Not Started | —
Control | Process has been handed off to the process owner | Not Started | —