## Dashboard
QUALITY GATE DASHBOARD
Latest release v4.19 (Ship) · Delivery data through Sep 2026 · 9 required gates in the Definition of Done
RELEASE QUALITY
LATEST RELEASE |  |  | PASS RATE · LATEST RELEASE |  |  | REQUIRED FAILS · LATEST RELEASE |  |  | AUTOMATION COVERAGE
v4.19 |  |  | 100% |  |  | 0 |  |  | 50%
Ship · 5 Oct 2026 |  |  | 10 of 10 checks passed |  |  | 0 required not logged · 0 fails in total |  |  | 5 of 10 Definition of Done items
DELIVERY PERFORMANCE (DORA) · latest month vs prior month
DEPLOYMENTS PER WEEK |  |  | MEDIAN LEAD TIME (DAYS) |  |  | CHANGE FAILURE RATE |  |  | MEDIAN TIME TO RESTORE (HRS)
14 |  |  | 1 |  |  | 8.333% |  |  | 0.6
Elite · prior 13.1 |  |  | Elite · prior 1.5 |  |  | High · prior 8.6% |  |  | Elite · prior 0.8
RELEASE SCORECARD · latest 6 releases | [10 empty] | CHART DATA (oldest to newest; do not edit)
Release | Date | Pass | Fail | Waived | Checks | Required fails | Required not logged | Pass rate | Verdict |  | Release | Pass | Fail | Waived
v4.19 | 2026-10-05 | 10 | 0 | 0 | 10 | 0 | 0 | 100% | Ship |  | v4.14 | 8 | 1 | 0
v4.18 | 2026-09-14 | 7 | 2 | 0 | 9 | 2 | 0 | 77.78% | Blocked |  | v4.15 | 8 | 1 | 0
v4.17 | 2026-08-10 | 8 | 1 | 0 | 9 | 1 | 0 | 88.89% | Blocked |  | v4.16 | 9 | 0 | 1
v4.16 | 2026-07-20 | 9 | 0 | 1 | 10 | 0 | 0 | 100% | Ship with waivers |  | v4.17 | 8 | 1 | 0
v4.15 | 2026-06-29 | 8 | 1 | 0 | 9 | 1 | 0 | 88.89% | Blocked |  | v4.18 | 7 | 2 | 0
v4.14 | 2026-06-08 | 8 | 1 | 0 | 9 | 1 | 0 | 88.89% | Blocked |  | v4.19 | 10 | 0 | 0
TRENDS
MOST-FAILED DEFINITION OF DONE ITEMS
ID | Times failed | Item | [6 empty] | Required? | Last result
D08 | 3 | Rollback plan tested or confirmed | [6 empty] | Yes | Pass
D05 | 2 | Integration tests pass | [6 empty] | Yes | Pass
Verdict: Blocked = a required item failed · Incomplete = a required item has no result logged · Ship with waivers = no required fail but a waiver · Ship = every required item passed. DORA bands are editable on Delivery Metrics.
Formulas:
Date = IF(ANCHORARRAY([LATEST RELEASE])="","",MAXIFS(GateLog[Date],GateLog[Release],ANCHORARRAY([LATEST RELEASE])))

## How-To
DEFINITION OF DONE AND QUALITY GATES
How to use this workbook
WHAT THIS WORKBOOK IS
Purpose | A working set for delivery quality: a written definition of done, a release gate log that records the result of every check, and a monthly log of the four DORA delivery metrics. A dashboard rolls it up into a verdict per release.
HOW TO USE IT
1 Definition of Done | List the items a change or release must satisfy, whether each is automated or manual, the evidence expected, and whether it is required. Agree it with the team.
2 Release Gate Log | For each release, record the result of each item as Pass, Fail or Waived, with an owner and a note. Item name and Required? look up from the Definition of Done.
3 Delivery Metrics | Each month, enter deployments, failed deployments, median lead time and median time to restore. Change failure rate, deployments per week and the 3-month rolling rate calculate.
4 Dashboard | Read-only summary: latest release verdict, scorecard, DORA tiles, trends and most-failed items. Everything on it is formula-driven.
COLOR LEGEND
Input | Yellow cells are inputs. Type here.
Calculated | Grey cells contain formulas. Do not overwrite them.
Pass / Ship | Green. The check passed, or the release can ship.
Waived / Ship with waivers | Amber. A check was waived on purpose; record who accepted the risk in Notes.
Fail / Blocked | Red. A check failed, or a required item failed so the release is blocked.
HOW THINGS ARE CALCULATED
Release verdict | Blocked if any required item has a Fail. Otherwise Incomplete if a required item has no result logged for that release. Otherwise Ship with waivers if anything was Waived. Otherwise Ship.
Pass rate | Passed checks divided by checks that were not waived, for each release.
Row flags | Release Gate Log column I flags a failed required item (Blocker), a Fail or Waived row with no note, a duplicate item in one release, and an Item ID that is not on the Definition of Done.
Change failure rate | Failed deployments divided by deployments. The 3-month rolling rate pools the latest three months, so a quiet month does not distort it.
Deployments per week | Deployments divided by the number of weeks in the month (days in month divided by 7).
DORA bands | Elite, High, Medium and Low cut-offs sit in the yellow cells on Delivery Metrics. Defaults approximate published DORA research; change them to your own standard.
GOOD PRACTICE
Define consistently | DORA definitions and benchmarks have been refined over time. Define each measure the same way every month and compare mainly with your own trend.
Fast feedback | Use quality gates to give fast feedback. Avoid setting targets on proxies such as code coverage.
Placeholders | The example items, releases and months show how the formulas work. Overwrite them with your own.
Release names | Enter release names as text, for example v4.10, so a trailing zero is never lost.
IMPORTANT
Educational template | It supports a software or IT team's review and planning. It is not security, legal, compliance or engineering advice and does not replace your organization's policies and controls. Avoid entering customer data, credentials or other sensitive information.

## Definition of Done
DEFINITION OF DONE
Agree what “done” means for a change and a release. Yellow cells are inputs; grey columns calculate from the Release Gate Log. Example items are placeholders.
10 items · 9 required · 5 automated · 5 manual
ID | Item | Applies to | Category | Gate type | Evidence expected | Required? | Times checked | Fails | Last result
D01 | Change reviewed by at least one other engineer | Change | Code | Manual | Approved pull request | Yes | 6 | 0 | Pass
D02 | Unit tests added or updated and passing | Change | Tests | Automated | CI result | Yes | 6 | 0 | Pass
D03 | Static analysis has no new high-severity findings | Change | Code | Automated | CI result | Yes | 6 | 0 | Pass
D04 | Dependency and secret scans pass | Change | Security | Automated | CI result | Yes | 6 | 0 | Pass
D05 | Integration tests pass | Release | Tests | Automated | Pipeline result | Yes | 6 | 2 | Pass
D06 | Performance check within agreed limits | Release | Tests | Automated | Pipeline result | Yes | 6 | 0 | Pass
D07 | Monitoring and alerts updated for new behavior | Release | Operations | Manual | Dashboard and alert links | Yes | 6 | 0 | Pass
D08 | Rollback plan tested or confirmed | Release | Operations | Manual | Runbook link | Yes | 6 | 3 | Pass
D09 | Documentation and release notes updated | Release | Docs | Manual | Links | Yes | 6 | 0 | Pass
D10 | Feature flag or canary configured for risky changes | Release | Operations | Manual | Configuration | No | 2 | 0 | Pass

## Release Gate Log
RELEASE GATE LOG
One row per item per release. Enter the Item ID from the Definition of Done; Item and Required? look up. Fails and waivers need a note. Example rows are placeholders.
56 checks · 6 releases · 5 failed · 1 waived · 5 rows need attention
Release | Date | Item ID | Item | Required? | Result | Owner | Notes | Flag | VERDICT RULES
v4.14 | 2026-06-08 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead |  |  | Blocked | Any required item has a Fail
v4.14 | 2026-06-08 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead |  |  | Incomplete | A required item has no result logged for the release
v4.14 | 2026-06-08 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead |  |  | Ship with waivers | No required Fail, but at least one Waived
v4.14 | 2026-06-08 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead |  |  | Ship | Every required item passed
v4.14 | 2026-06-08 | D05 | Integration tests pass | Yes | Pass | Release lead
v4.14 | 2026-06-08 | D06 | Performance check within agreed limits | Yes | Pass | Release lead |  |  | ROW FLAGS
v4.14 | 2026-06-08 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead |  |  | Blocker | A required item failed
v4.14 | 2026-06-08 | D08 | Rollback plan tested or confirmed | Yes | Fail | Release lead | Rollback not rehearsed in staging | Blocker | Add note | A Fail or Waived row has no note
v4.14 | 2026-06-08 | D09 | Documentation and release notes updated | Yes | Pass | Release lead |  |  | Duplicate | Same item logged twice for one release
v4.15 | 2026-06-29 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead |  |  | Unknown item | Item ID is not on the Definition of Done
v4.15 | 2026-06-29 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D05 | Integration tests pass | Yes | Fail | Release lead | Flaky integration suite; rerun pending | Blocker
v4.15 | 2026-06-29 | D06 | Performance check within agreed limits | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D08 | Rollback plan tested or confirmed | Yes | Pass | Release lead
v4.15 | 2026-06-29 | D09 | Documentation and release notes updated | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D05 | Integration tests pass | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D06 | Performance check within agreed limits | Yes | Waived | Release lead | Perf baseline rebuild; approved by eng manager
v4.16 | 2026-07-20 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D08 | Rollback plan tested or confirmed | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D09 | Documentation and release notes updated | Yes | Pass | Release lead
v4.16 | 2026-07-20 | D10 | Feature flag or canary configured for risky changes | No | Pass | Release lead
v4.17 | 2026-08-10 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D05 | Integration tests pass | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D06 | Performance check within agreed limits | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead
v4.17 | 2026-08-10 | D08 | Rollback plan tested or confirmed | Yes | Fail | Release lead | Rollback runbook out of date | Blocker
v4.17 | 2026-08-10 | D09 | Documentation and release notes updated | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D05 | Integration tests pass | Yes | Fail | Release lead | Integration environment unavailable | Blocker
v4.18 | 2026-09-14 | D06 | Performance check within agreed limits | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead
v4.18 | 2026-09-14 | D08 | Rollback plan tested or confirmed | Yes | Fail | Release lead | Rollback runbook out of date | Blocker
v4.18 | 2026-09-14 | D09 | Documentation and release notes updated | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D01 | Change reviewed by at least one other engineer | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D02 | Unit tests added or updated and passing | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D03 | Static analysis has no new high-severity findings | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D04 | Dependency and secret scans pass | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D05 | Integration tests pass | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D06 | Performance check within agreed limits | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D07 | Monitoring and alerts updated for new behavior | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D08 | Rollback plan tested or confirmed | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D09 | Documentation and release notes updated | Yes | Pass | Release lead
v4.19 | 2026-10-05 | D10 | Feature flag or canary configured for risky changes | No | Pass | Release lead

## Delivery Metrics
DELIVERY METRICS (DORA)
Enter one row per month (first day of the month). Grey columns calculate. Cells are shaded by DORA performance band (see right). Example rows are placeholders.
September 2026 latest · 6 months logged · Overall change failure rate 10.9%
Month (first day) | Deployments | Failed deployments | Median lead time (days) | Median time to restore (hours) | Change failure rate | Deployments per week | Change failure rate (3-mo rolling) | DORA PERFORMANCE BANDS (edit thresholds in yellow)
2026-04-01 | 40 | 6 | 3 | 2 | 15% | 9.3333 | 15% | Metric | Better when | Elite | High | Medium | Latest | Prior | Band
2026-05-01 | 44 | 6 | 3 | 1.8 | 13.64% | 9.9355 | 14.29% | Deployments per week | Higher | 7 | 1 | 0.25 | 14 | 13.0968 | Elite
2026-06-01 | 48 | 6 | 2 | 1.3 | 12.5% | 11.2 | 13.64% | Median lead time (days) | Lower | 1 | 7 | 30 | 1 | 1.5 | Elite
2026-07-01 | 52 | 5 | 2 | 1 | 9.615% | 11.7419 | 11.81% | Change failure rate | Lower | 5% | 10% | 15% | 8.333% | 8.621% | High
2026-08-01 | 58 | 5 | 1.5 | 0.8 | 8.621% | 13.0968 | 10.13% | Median time to restore (hours) | Lower | 1 | 24 | 168 | 0.6 | 0.8 | Elite
2026-09-01 | 60 | 5 | 1 | 0.6 | 8.333% | 14 | 8.824% | Cut-offs: anything beyond Medium is Low. Defaults approximate DORA research; set your own standard.
[8 empty] | Latest month with data | 2026-09-01
[8 empty] | Prior month | 2026-08-01
CHART DATA (latest 6 months, feeds the charts; do not edit)
[8 empty] | Month | Change failure rate | Change failure rate (3-mo rolling) | Deployments per week | Median lead time (days) | Median time to restore (hours)
[8 empty] | 2026-04-01 | 15% | 15% | 9.3333 | 3 | 2
[8 empty] | 2026-05-01 | 13.64% | 14.29% | 9.9355 | 3 | 1.8
[8 empty] | 2026-06-01 | 12.5% | 13.64% | 11.2 | 2 | 1.3
[8 empty] | 2026-07-01 | 9.615% | 11.81% | 11.7419 | 2 | 1
[8 empty] | 2026-08-01 | 8.621% | 10.13% | 13.0968 | 1.5 | 0.8
[8 empty] | 2026-09-01 | 8.333% | 8.824% | 14 | 1 | 0.6
Formulas:
Deployments per week = IF(OR([Month (first day)]="",NOT(ISNUMBER([Deployments]))),"",[Deployments]/(DAY(EOMONTH([Month (first day)],0))/7))