## Dashboard
Sample project: Level 3 corridor renovation
Last Planner dashboard ¦ Report date Oct 7, 2026 ¦ Prepared by Superintendent
Chart and list helpers (calculated, do not edit)
LATEST WEEK PPC |  | 4-WEEK PPC | OVERALL PPC | LOOKAHEAD READY |  | BLOCKED ACTIVITIES |  | TOP MISS REASON
87.5% |  | 83.33% | 83.33% | 40% |  | 3 |  | Materials |  | Last reported week # | 3
Week of Oct 19 |  | On target (80%) | 20 of 24 assignments completed | 2 of 5 activities ready |  | 0 late, 2 due soon |  | 1 miss (25% of all) |  | First week shown # | 1
PPC by week vs target (12-week view) |  |  |  | Why assignments were missed (Pareto) | [5 empty] | Week | PPC | Target | Row #
[10 empty] | Oct 5 | 75% | 80% | 1
[10 empty] | Oct 12 | 87.5% | 80% | 2
[10 empty] | Oct 19 | 87.5% | 80% | 3
[10 empty] | Oct 26 | #N/A | 80% | 4
[10 empty] | Nov 2 | #N/A | 80% | 5
[10 empty] | Nov 9 | #N/A | 80% | 6
[10 empty] | Nov 16 | #N/A | 80% | 7
[10 empty] | Nov 23 | #N/A | 80% | 8
[10 empty] | Nov 30 | #N/A | 80% | 9
[10 empty] | Dec 7 | #N/A | 80% | 10
[10 empty] | Dec 14 | #N/A | 80% | 11
[10 empty] | Dec 21 | #N/A | 80% | 12
[10 empty] | Reason | Missed | Cumulative % | Sort key
[10 empty] | Materials | 1 | 25% | 1.0086
Lookahead readiness by week |  |  |  | Readiness detail | [5 empty] | Prerequisite work | 1 | 50% | 1.0085
|  |  |  | Window | Ready | Blocked | Activities | % ready | Week of | Design info / RFI | 1 | 75% | 1.0084
|  |  |  | Wk 1 | 0 | 0 | 0 |  | 2026-10-05 | Labor / crew | 1 | 100% | 1.0083
|  |  |  | Wk 2 | 1 | 1 | 2 | 50% | 2026-10-12 | Equipment | 0 | 100% | 0.0082
|  |  |  | Wk 3 | 1 | 1 | 2 | 50% | 2026-10-19 | Weather | 0 | 100% | 0.0081
|  |  |  | Wk 4 | 0 | 1 | 1 | 0% | 2026-10-26 | Owner / inspector | 0 | 100% | 0.008
|  |  |  | Wk 5 | 0 | 0 | 0 |  | 2026-11-02 | Other | 0 | 100% | 0.0079
|  |  |  | Wk 6 | 0 | 0 | 0 |  | 2026-11-09
|  |  |  | Total | 2 | 3 | 5 | 40%
Blocked activities to clear next (soonest need-by first)
ID | Activity |  | Constraint | Owner |  | Need-by | Days left | Constraint detail |  | Blocked sort key | Table row #
A02 | Rough-in plumbing, level 3 |  | Materials | Procurement |  | 2026-10-09 | 2 | Copper fittings due from supplier |  | 46304.0001 | 2
A03 | Install duct, level 3 ceiling |  | Design info / RFI | Project engineer |  | 2026-10-14 | 7 | RFI 214 open on duct routing |  | 46309.0001 | 3
A05 | Paint level 2 corridors |  | Access / space | Foreman |  | 2026-10-22 | 15 | Floor protection in place |  | 46317.0001 | 5
Formulas:
BLOCKED ACTIVITIES = IF([PPC]="","",IF(ISNUMBER(INDEX(Lookahead[Need-by date],[PPC])),INDEX(Lookahead[Need-by date],[PPC]),"none set"))

## How-To
LAST PLANNER WORK PLAN
How to use this workbook
What this workbook is
A working set for the Last Planner System: a lookahead where you screen upcoming activities for constraints, a weekly work plan of crew commitments, and a PPC log that calculates Percent Plan Complete and counts the reasons for misses. The Dashboard turns it all into a one-page view for the weekly meeting.
The workflow
Step | Sheet | What you do
1 | Setup | Enter the project name, the first week of the log, and your PPC target. Rename or add dropdown items on the Lists sheet if your trades or reasons differ.
2 | Lookahead | List activities starting inside the lookahead window (6 weeks by default). For each, pick a constraint, name an owner and set a need-by date. An activity is Ready when it has no constraint or the constraint is Cleared.
3 | Weekly Work Plan | List the assignments crews commit to, using only Ready work (enter the Activity ID and the Ready check confirms it). At week end mark Completed Yes or No, and choose a reason for every No.
4 | PPC Log | Nothing to enter. Planned, Completed, PPC, rolling 4-week PPC and misses by reason calculate from the Weekly Work Plan.
5 | Dashboard | Open it in the weekly meeting: PPC against target, why plans fail, readiness by week, and the blocked activities to clear next.
Color key
| Cream | Input cell. Type or pick a value here.
| Grey | Calculated cell. It holds a formula, so do not type over it.
| Ready | Activity has no open constraint, or the assignment's activity is Ready.
| Blocked / Due soon | Open constraint; flagged Due soon when the need-by date is close.
| Late / Add reason | Past its need-by date, or a missed assignment with no reason recorded.
Good practice
• | PPC measures the reliability of promises, not progress. Track it alongside schedule progress, and use it to learn as a team rather than to rank crews.
• | Use the first day of the week (for example, Monday) consistently in every date column, and set the same first week on Setup.
• | The example rows are placeholders. Overwrite the cream input cells; leave the grey formula columns in place.
• | Review misses weekly: the Pareto on the Dashboard shows which reasons to fix first.
Important
Educational template. It supports a construction team's planning and quality tracking. It is not engineering, legal, contract, building-code, or safety-compliance advice and does not replace your project documents, applicable codes, or the judgment of qualified professionals.

## Setup
SETUP
Project settings used across the workbook. Change a value once and every sheet updates.
Project settings | Value | What it does
Project name | Sample project: Level 3 corridor renovation | Shown at the top of the Dashboard.
Prepared by | Superintendent | Shown on the Dashboard.
First week of the log (week of) | 2026-10-05 | Week 1 of the PPC Log. Use the first day of the week (for example, Monday) and keep it consistent.
PPC target | 80% | Target line on the PPC trend chart and the on-target / below-target call-out.
Lookahead window (weeks) | 6 | How many weeks ahead the Lookahead screens. Activities starting later are marked Beyond window.
Due-soon threshold (days) | 7 | Blocked activities within this many days of their need-by date are flagged Due soon.
Report date | 2026-10-07 | Defaults to today. Type a date to freeze the report at that day.
Current week of | 2026-10-05 | Calculated: the Monday of the report date's week.
Dropdown lists live on the Lists sheet. Cream cells are inputs; grey cells are calculated.
Formulas:
Value = [Value, row above]-WEEKDAY([Value, row above],3)

## Lookahead
6-WEEK LOOKAHEAD
Screen every activity starting in the next 6 weeks. Ready = no constraint, or the constraint is Cleared. Example rows are placeholders; overwrite them.
Ready 2 Blocked 3 Late 0 Due soon 2
ID | Activity | Trade | Planned start (week of) | Constraint | Constraint detail | Owner | Need-by date | Status | Ready? | Flag | Window | Days to need-by
A01 | Frame corridor walls, level 3 | Framing | 2026-10-12 | None |  | Foreman |  | Cleared | Ready |  | Wk 2
A02 | Rough-in plumbing, level 3 | Plumbing | 2026-10-12 | Materials | Copper fittings due from supplier | Procurement | 2026-10-09 | Open | Blocked | Due soon | Wk 2 | 2
A03 | Install duct, level 3 ceiling | Mechanical | 2026-10-19 | Design info / RFI | RFI 214 open on duct routing | Project engineer | 2026-10-14 | Open | Blocked | Due soon | Wk 3 | 7
A04 | Hang drywall, level 3 east | Drywall | 2026-10-19 | Prerequisite work | Above-ceiling inspection needed | Superintendent | 2026-10-16 | Cleared | Ready |  | Wk 3 | 9
A05 | Paint level 2 corridors | Paint | 2026-10-26 | Access / space | Floor protection in place | Foreman | 2026-10-22 | Open | Blocked |  | Wk 4 | 15

## Weekly Work Plan
WEEKLY WORK PLAN
One row per assignment. Commit only Ready work (link it with Activity ID). At week end mark Completed, and give a reason for every No.
This week: 8 committed Needs attention: 0
Week of | Activity ID | Assignment | Trade | Committed? | Completed? | Reason if not completed | Ready check | Close-out check
2026-10-05 |  | Frame walls, zone 1 | Framing | Yes | Yes |  |  | OK
2026-10-05 |  | Rough-in electrical, zone 1 | Electrical | Yes | Yes |  |  | OK
2026-10-05 |  | Set duct hangers, zone 1 | Mechanical | Yes | Yes |  |  | OK
2026-10-05 |  | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes |  |  | OK
2026-10-05 |  | Frame walls, zone 2 | Framing | Yes | Yes |  |  | OK
2026-10-05 |  | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes |  |  | OK
2026-10-05 |  | Hang drywall, zone 1 | Drywall | Yes | No | Materials |  | OK
2026-10-05 |  | Insulate walls, zone 2 | Insulation | Yes | No | Prerequisite work |  | OK
2026-10-12 |  | Frame walls, zone 1 | Framing | Yes | Yes |  |  | OK
2026-10-12 |  | Rough-in electrical, zone 1 | Electrical | Yes | Yes |  |  | OK
2026-10-12 |  | Set duct hangers, zone 1 | Mechanical | Yes | Yes |  |  | OK
2026-10-12 |  | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes |  |  | OK
2026-10-12 |  | Frame walls, zone 2 | Framing | Yes | Yes |  |  | OK
2026-10-12 |  | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes |  |  | OK
2026-10-12 |  | Hang drywall, zone 1 | Drywall | Yes | Yes |  |  | OK
2026-10-12 |  | Insulate walls, zone 2 | Insulation | Yes | No | Design info / RFI |  | OK
2026-10-19 |  | Frame walls, zone 1 | Framing | Yes | Yes |  |  | OK
2026-10-19 |  | Rough-in electrical, zone 1 | Electrical | Yes | Yes |  |  | OK
2026-10-19 |  | Set duct hangers, zone 1 | Mechanical | Yes | Yes |  |  | OK
2026-10-19 |  | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes |  |  | OK
2026-10-19 |  | Frame walls, zone 2 | Framing | Yes | Yes |  |  | OK
2026-10-19 |  | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes |  |  | OK
2026-10-19 |  | Hang drywall, zone 1 | Drywall | Yes | No | Labor / crew |  | OK
2026-10-19 |  | Insulate walls, zone 2 | Insulation | Yes | Yes |  |  | OK

## PPC Log
PERCENT PLAN COMPLETE LOG
Everything here calculates from the Weekly Work Plan. Weeks run from the first week set on the Setup sheet. No input needed.
Week of | Planned | Completed | PPC | Missed | Missed without reason | Rolling 4 wk PPC | Summary | Value
2026-10-05 | 8 | 6 | 75% | 2 | 0 | 75% | Overall PPC | 83.33%
2026-10-12 | 8 | 7 | 87.5% | 1 | 0 | 81.25% | PPC target | 80%
2026-10-19 | 8 | 7 | 87.5% | 1 | 0 | 83.33% | Latest 4-week PPC | 83.33%
2026-10-26 | 0 | 0 |  | 0 | 0 |  | Latest reported week | 2026-10-19
2026-11-02 | 0 | 0 |  | 0 | 0 |  | Assignments committed | 24
2026-11-09 | 0 | 0 |  | 0 | 0 |  | Assignments completed | 20
2026-11-16 | 0 | 0 |  | 0 | 0 |  | Misses without a reason | 0
2026-11-23 | 0 | 0 |  | 0 | 0
2026-11-30 | 0 | 0 |  | 0 | 0 |  | Reason for miss | Missed | % of misses | Sort key (helper)
2026-12-07 | 0 | 0 |  | 0 | 0 |  | Materials | 1 | 25% | 1.0086
2026-12-14 | 0 | 0 |  | 0 | 0 |  | Prerequisite work | 1 | 25% | 1.0085
2026-12-21 | 0 | 0 |  | 0 | 0 |  | Design info / RFI | 1 | 25% | 1.0084
2026-12-28 | 0 | 0 |  | 0 | 0 |  | Labor / crew | 1 | 25% | 1.0083
2027-01-04 | 0 | 0 |  | 0 | 0 |  | Equipment | 0 | 0% | 0.0082
2027-01-11 | 0 | 0 |  | 0 | 0 |  | Weather | 0 | 0% | 0.0081
2027-01-18 | 0 | 0 |  | 0 | 0 |  | Owner / inspector | 0 | 0% | 0.008
2027-01-25 | 0 | 0 |  | 0 | 0 |  | Other | 0 | 0% | 0.0079
2027-02-01 | 0 | 0 |  | 0 | 0
2027-02-08 | 0 | 0 |  | 0 | 0
2027-02-15 | 0 | 0 |  | 0 | 0 |  | Total with a reason | 4 | 100%
2027-02-22 | 0 | 0 |  | 0 | 0
2027-03-01 | 0 | 0 |  | 0 | 0
2027-03-08 | 0 | 0 |  | 0 | 0
2027-03-15 | 0 | 0 |  | 0 | 0
2027-03-22 | 0 | 0 |  | 0 | 0
2027-03-29 | 0 | 0 |  | 0 | 0
2027-04-05 | 0 | 0 |  | 0 | 0
2027-04-12 | 0 | 0 |  | 0 | 0
2027-04-19 | 0 | 0 |  | 0 | 0
2027-04-26 | 0 | 0 |  | 0 | 0
2027-05-03 | 0 | 0 |  | 0 | 0
2027-05-10 | 0 | 0 |  | 0 | 0
2027-05-17 | 0 | 0 |  | 0 | 0
2027-05-24 | 0 | 0 |  | 0 | 0
2027-05-31 | 0 | 0 |  | 0 | 0
2027-06-07 | 0 | 0 |  | 0 | 0
2027-06-14 | 0 | 0 |  | 0 | 0
2027-06-21 | 0 | 0 |  | 0 | 0
2027-06-28 | 0 | 0 |  | 0 | 0
2027-07-05 | 0 | 0 |  | 0 | 0
2027-07-12 | 0 | 0 |  | 0 | 0
2027-07-19 | 0 | 0 |  | 0 | 0
2027-07-26 | 0 | 0 |  | 0 | 0
2027-08-02 | 0 | 0 |  | 0 | 0
2027-08-09 | 0 | 0 |  | 0 | 0
2027-08-16 | 0 | 0 |  | 0 | 0
2027-08-23 | 0 | 0 |  | 0 | 0
2027-08-30 | 0 | 0 |  | 0 | 0
2027-09-06 | 0 | 0 |  | 0 | 0
2027-09-13 | 0 | 0 |  | 0 | 0
2027-09-20 | 0 | 0 |  | 0 | 0
2027-09-27 | 0 | 0 |  | 0 | 0
Formulas:
Week of = FirstWeek+7*(ROW()-ROW(PPCLog[[#Headers],[Week of]])-1)
Value = IFERROR(LOOKUP(2,1/(PPCLog[Planned]>0),PPCLog[Week of]),"")

## Lists
DROPDOWN LISTS
Add or rename items inside each table. The dropdowns on every sheet read from these lists and update automatically.
Constraint | Reason for miss | Trade | Status | Yes / No
None | Materials | Framing | Open | Yes
Materials | Prerequisite work | Electrical | Cleared | No
Design info / RFI | Design info / RFI | Mechanical
Prerequisite work | Labor / crew | Plumbing
Labor / crew | Equipment | Fire-stopping
Equipment | Weather | Drywall
Access / space | Owner / inspector | Insulation
Permit / inspection | Other | Paint
Sitework
Concrete
Roofing
Glazing
Flooring
Sprinkler
Controls
General