## How-To
MANAGEMENT OF CHANGE REGISTER
Request, track, and close out every change to your facility, process, or equipment, with nothing slipping past its deadline.
HOW IT WORKS
1 MOC Request Form | Describe the change, its technical basis, and the hazard review. Print it (set to one A4 page) or copy the fields into your own system.
2 MOC Register | Log every change. Record hazard review, approval, documents, training, and pre-startup review as Yes or No. Days open and every flag calculate automatically.
3 Dashboard | Review open, overdue, and expired items, performance, and the 'Action required' list. Nothing to type; it reads from the register.
COLOUR KEY
Input | Yellow cells are yours to complete.
Calculated | Grey cells hold formulas. Do not overwrite them.
Flag | Red = overdue or data issue. Amber = expired temporary change or incomplete checklist. Green = ready.
DEFINITIONS
Change types | Permanent: lasting change. Temporary: has an end date and an owner. Emergency: made urgently, with review completed after. Replacement in kind: identical to what it replaces; define narrowly and in writing.
Status | Open > Approved > Implemented > Closed. Use Cancelled if the change is withdrawn.
Ready to close? | Ready when hazard review, approval, documents, training, and PSSR are all Yes. Closed and cancelled rows show n/a.
Overdue? | Open change past its target close date and not yet closed.
Temporary expired? | Temporary change past its end date and not yet closed. Review, extend with approval, or remove.
Data check | Flags duplicate MOC numbers, temporary changes with no end date, closed changes with no close date, and closed changes with an incomplete checklist.
GOOD PRACTICE
Examples | The four example rows are placeholders showing how the flags behave. Overwrite or delete them.
Temporary changes | Give every temporary change an end date and an owner.
Adding changes | Type in the first empty row of the register. The table, formulas, dropdowns, and dashboard extend automatically.
Today's date | Overdue and expired flags depend on today's date, so they refresh each time the file opens.
IMPORTANT
Educational template. It supports an asset-management or process-safety team's discussion and documentation. It is not engineering, legal, safety-compliance, or regulatory advice and does not replace your site's procedures, applicable regulations, or the judgment of qualified professionals. Your site's MOC procedure takes precedence; edit the checklist to match it.

## MOC Request Form
MANAGEMENT OF CHANGE REQUEST
Complete before the change is made. Keep answers specific. Fill the yellow cells only.
Item | What to include | Your entry
1 IDENTIFICATION
MOC number | Unique ID from the register, for example MOC-2605.
Date requested | Date the request was raised.
Requester | Name and role.
Area, unit, or equipment | Where the change applies, with tag numbers if known.
Change type | Pick one. Define 'replacement in kind' narrowly and in writing.
Temporary end date and owner | Required for Temporary changes. Name who removes it.
2 THE CHANGE
Description of the change | What is being changed, and why?
Technical basis | Design basis, calculations, and drawings affected.
3 HAZARD REVIEW
Safety, health, and environmental impact | What new hazards could this create? What existing protections could it affect (alarms, trips, relief, procedures)?
Hazard review method and participants | For example What-If, checklist, or HAZOP node, and who took part. Include someone independent of the request.
Hazard review completed? | Select Yes only once findings are recorded and actioned.
4 IMPLEMENTATION READINESS
Documents to update | P&IDs, setpoint lists, operating procedures, maintenance procedures, training material.
Training required | Who must be told or trained, and by when.
Pre-startup safety review | Who confirmed the change is ready, and how.
5 APPROVALS
Role | Name | Signature and date
Requester
Technical reviewer
Safety / operations
Final approver
6 CLOSE-OUT
Close-out | Date closed, and confirmation that documents are updated and any temporary change is removed.

## MOC Register
MOC REGISTER
Log every change from request to close-out. Calculated columns (Q:U) update automatically; add new rows directly below the table and they expand it.
Input | Calculated
MOC # | Date opened | Description | Area / unit | Change type | Requester | Owner | Hazard review done | Approved | Documents updated | Training complete | PSSR done | Status | Target close date | Date closed | Temporary end date | Days open | Overdue? | Temporary expired? | Ready to close? | Data check
MOC-2601 | 2026-08-03 | Replace level transmitter LT-101 with a different range model | Separator area | Permanent | Instrument tech | Process engineer | Yes | Yes | Yes | Yes | Yes | Closed | 2026-08-24 | 2026-08-21 |  | 18 |  |  | n/a | OK
MOC-2602 | 2026-08-20 | Temporary jumper on low-flow trip during compressor commissioning | Compressor station | Temporary | Operations | Operations manager | Yes | Yes | No | Yes | No | Implemented | 2026-09-10 |  | 2026-09-15 | 48 | Overdue | Expired - review | Incomplete | OK
MOC-2603 | 2026-09-02 | Change relief valve set pressure after re-rating | Vessel V-200 | Permanent | Process engineer | Process engineer | Yes | No | No | No | No | Open | 2026-10-15 |  |  | 35 |  |  | Incomplete | OK
MOC-2604 | 2026-09-12 | Substitute gasket material on hot oil line | Heater area | Permanent | Maintenance | Maintenance lead | No | No | No | No | No | Open | 2026-10-01 |  |  | 25 | Overdue |  | Incomplete | OK
Formulas:
Days open = IF(MOCRegister[[#This Row],[Date opened]]="","",IF(ISNUMBER(MOCRegister[[#This Row],[Date closed]]),MOCRegister[[#This Row],[Date closed]]-MOCRegister[[#This Row],[Date opened]],TODAY()-MOCRegister[[#This Row],[Date opened]]))

## Dashboard
MOC DASHBOARD
As of 07 Oct 2026 ¦ Live from the MOC Register - nothing on this sheet needs typing
CHANGES LOGGED |  | OPEN CHANGES |  | OVERDUE |  | TEMPORARY EXPIRED |  | READY TO CLOSE |  | CLOSED
4 |  | 3 |  | 2 |  | 1 |  | 0 |  | 1
all time |  | 75% of logged |  | 67% of open |  | past end date, review |  | open, checklist complete |  | 25% of logged
AVG DAYS TO CLOSE |  | ON-TIME CLOSE RATE |  | AVG AGE OF OPEN |  | ACTIVE TEMPORARY |  | EMERGENCY SHARE |  | DATA ISSUES
18 |  | 100% |  | 36 |  | 1 |  | 0% |  | 0
closed changes |  | closed by target date |  | days, open changes |  | not yet removed/closed |  | of all changes |  | see Register column U
CHANGES BY STATUS |  | Count | % of total
Open |  | 2 | 50%
Approved |  | 0 | 0%
Implemented |  | 1 | 25%
Closed |  | 1 | 25%
Cancelled |  | 0 | 0%
Total |  | 4 | 100%
CHANGES BY TYPE |  | Count | % of total
Permanent |  | 3 | 75%
Temporary |  | 1 | 25%
Emergency |  | 0 | 0%
Replacement in kind |  | 0 | 0%
Total |  | 4 | 100%
ACTION REQUIRED - OVERDUE OR EXPIRED CHANGES (OLDEST FIRST) | [10 empty] | Helper
MOC # | Description |  |  |  | Owner |  | Status | Target close | Days open | Flag | Row key
MOC-2602 | Temporary jumper on low-flow trip during compressor commissioning |  |  |  | Operations manager |  | Implemented | 2026-09-10 | 48 | Overdue + Temp expired | 48.0001
MOC-2604 | Substitute gasket material on hot oil line |  |  |  | Maintenance lead |  | Open | 2026-10-01 | 25 | Overdue | 25.0001
Formulas:
READY TO CLOSE = IF([Row key]="","",INDEX(MOCRegister[Target close date],ROUND(([Row key]-INT([Row key]))*100000,0)-ROW(MOCRegister[#Headers])))