## How-To
PUNCH LIST & INSPECTION TRACKER
How to use this workbook
WHAT THIS WORKBOOK DOES
A construction quality tracker in one file: an inspection and test plan (ITP) of hold, witness and review points; a punch list that calculates days open, overdue and due-soon flags; and a Dashboard that summarizes both by status, category, priority, trade and age.
WORKFLOW
Step | Tab | What to do
1. Set up lists | Lists → | Review categories, trades, priorities and statuses. Set the closed status and the due-soon window. Every dropdown and the Dashboard read from here.
2. Plan inspections | Inspection Plan → | List each critical activity with its spec reference, point type (Hold, Witness or Review), frequency, responsible person and acceptance criteria. Agree it with the project team before work starts.
3. Log punch items | Punch List → | Add one row per item: location, trade, description, category, priority, assignee and due date. Optionally link an item to an inspection with ITP ref.
4. Update as you go | Inspection Plan → | Change Status as work proceeds. When an item is closed, enter the Date closed. Record each inspection's Status and Date inspected on the Inspection Plan.
5. Review | Dashboard → | Check KPIs, aging and overdue items weekly. Use the category and trade tables to find where problems start, then fix them at the source.
COLOUR KEY
Input cell | Input | Type or pick a value here (yellow fill, blue text).
Calculated cell | Calculated | Contains a formula. Do not overwrite (grey fill).
Overdue | Overdue | Item is not closed and its due date is before the as-of date.
Due soon | Due soon | Item is not closed and is due within the due-soon window.
Date mismatch | Mismatch | Status is Closed with no Date closed, or a Date closed on an item that is not closed.
KEY DEFINITIONS
Term |  | Meaning
Hold point |  | Work must stop until the inspection is done and approved.
Witness point |  | The inspector is invited to attend; work may proceed after the agreed notice period if they do not.
Review point |  | A document or record review, such as test results or a sample sign-off.
Days open |  | Date closed (or the as-of date if still open) minus Date found.
Age bucket |  | Open items grouped by days open. Thresholds are set on the Lists tab.
As-of date |  | Today, unless you enter an override on the Lists tab to report as at another day.
PUNCH LIST FIELD GUIDE
Column | Type | Notes
ID | Input | Unique reference, e.g. P001. Duplicates are highlighted.
Date found / Due date | Input | Valid dates only. Due date cannot be before Date found.
Location / zone, Description | Input | Be specific enough for the trade to find and fix the item.
Trade, Category, Priority, Status | Dropdown | Choices come from the Lists tab.
Assigned to | Input | Person or crew responsible for the fix.
Date closed | Input | Enter when the item passes recheck. Cannot be before Date found.
ITP ref | Dropdown | Optional link to an inspection ID on the Inspection Plan.
Notes / photo ref | Input | Photo file name, RFI number or any other reference.
Days open, Overdue?, Days overdue, Age bucket | Calculated | Formulas fill automatically for new rows.
GOOD PRACTICE
• Keep the ITP and punch list consistent with your contract documents and specifications, which take precedence. • The example rows are placeholders. Overwrite them with your own data. • Add new rows directly beneath either table; formulas, dropdowns and formatting extend automatically. • To add a new category, trade, priority or status, add it on the Lists tab and add a matching row to the Dashboard table. • Analyze categories and causes to fix problems at the source on the next project, not just to close items.
Educational template. It supports a construction team's planning and quality tracking. It is not engineering, legal, contract, building-code, or safety-compliance advice and does not replace your project documents, applicable codes, or the judgment of qualified professionals.

## Dashboard
PUNCH LIST & INSPECTION DASHBOARD
As of October 7, 2026 |  |  |  |  | ✔ All totals reconcile to items logged
ITEMS LOGGED | OPEN ITEMS |  | % CLOSED |  | OVERDUE | DUE SOON |  | AVG DAYS TO CLOSE
8 | 5 |  | 37.5% |  | 5 | 0 |  | 10.6667
6 inspection points | 2 high priority |  | 3 of 8 closed |  | oldest 13 days late | due within 7 days |  | open items avg 20.4 days old
VISUAL SUMMARY
DETAIL TABLES
Items by status |  |  |  |  | Items by priority
Status | Items | % of total | Overdue | Avg days open | Priority | Open | Closed | Overdue | Total
Open | 3 | 37.5% | 3 | 19.6667 | High | 2 | 0 | 2 | 2
In progress | 1 | 12.5% | 1 | 21 | Medium | 2 | 2 | 2 | 4
Ready for recheck | 1 | 12.5% | 1 | 22 | Low | 1 | 1 | 1 | 2
Closed | 3 | 37.5% | 0 | 10.6667 | Total | 5 | 3 | 5 | 8
Total | 8 | 100% | 5 | 16.75
Items by category |  |  |  |  | Open items by age
Category | Open | Closed | Total | % closed | Age bucket | Open items | % of open | High priority | Overdue
Finishes | 2 | 2 | 4 | 50% | 0-7 days | 0 | 0% | 0 | 0
MEP | 1 | 1 | 2 | 50% | 8-14 days | 0 | 0% | 0 | 0
Doors and hardware | 1 | 0 | 1 | 0% | 15-30 days | 5 | 100% | 2 | 5
Cleaning | 1 | 0 | 1 | 0% | 31+ days | 0 | 0% | 0 | 0
Structural | 0 | 0 | 0 | – | Total | 5 | 100% | 2 | 5
Other | 0 | 0 | 0 | –
Total | 5 | 3 | 8 | 37.5%
Items by trade |  |  |  |  | Inspection points by type
Trade | Open | Overdue | Closed | Total | Point type | Total | Passed | Failed | Outstanding
Carpentry | 1 | 1 | 0 | 1 | Hold | 3 | 2 | 0 | 1
Cleaning | 1 | 1 | 0 | 1 | Witness | 1 | 0 | 0 | 1
Drywall | 0 | 0 | 1 | 1 | Review | 2 | 1 | 0 | 1
Electrical | 0 | 0 | 1 | 1 | Total | 6 | 3 | 0 | 3
Flooring | 1 | 1 | 0 | 1
Glazing | 0 | 0 | 0 | 0
Mechanical | 1 | 1 | 0 | 1
Paint | 1 | 1 | 1 | 2
Plumbing | 0 | 0 | 0 | 0
Roofing | 0 | 0 | 0 | 0
General contractor | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0
Total | 5 | 5 | 3 | 8

## Inspection Plan
INSPECTION AND TEST PLAN
List critical activities with their inspection point type, then record status as work is inspected. Agree the plan with the project team before work starts. Example rows are placeholders.
6 inspection points ¦ 3 passed ¦ 0 failed ¦ 3 outstanding
ID | Activity | Requirement / spec reference | Point type | Frequency | Responsible | Acceptance criteria | Records | Status | Date inspected | Remarks | Punch items | Open punch items
I01 | Reinforcement before concrete placement | Spec 03 20 00 | Hold | Each pour | Quality manager | Size, spacing, cover, and ties match drawings | Inspection checklist, photos | Passed | 2026-09-16 |  | 0 | 0
I02 | Pipe pressure test | Spec 22 05 00 | Witness | Each system | MEP superintendent | Holds test pressure for the specified time with no drop | Test certificate | Scheduled |  |  | 1 | 1
I03 | Concrete cylinder results | Spec 03 30 00 | Review | Each 7 and 28 days | Quality manager | Strength meets specified minimum | Lab reports | Passed | 2026-09-20 |  | 0 | 0
I04 | Drywall finish mock-up | Spec 09 29 00 | Hold | First room, each floor | Drywall foreman and GC | Finish level and joint quality match approved sample | Mock-up sign-off | Passed | 2026-09-18 |  | 0 | 0
I05 | Above-ceiling inspection | Spec 01 45 00 | Hold | Each floor | Superintendent | All MEP inspected and signed off before closing ceilings | Inspection checklist | Planned |  |  | 1 | 0
I06 | Door hardware installation | Spec 08 71 00 | Review | 10% sample per floor | Trade foreman | Operation, clearances, and fasteners as specified | Punch sheet | Planned |  |  | 1 | 1

## Punch List
PUNCH LIST
One row per item. Yellow cells are inputs; grey cells calculate. The table grows automatically as you add rows below it. Example rows are placeholders.
As of Oct 7, 2026 ¦ 8 items ¦ 5 open ¦ 5 overdue ¦ 0 due soon
ID | Date found | Location / zone | Trade | Description | Category | Priority | Assigned to | Due date | Status | Date closed | ITP ref | Notes / photo ref | Days open | Overdue? | Days overdue | Age bucket
P001 | 2026-09-14 | Level 2, Room 214 | Paint | Touch-up scuffs on corridor wall | Finishes | Low | Paint foreman | 2026-09-25 | Closed | 2026-09-22 |  |  | 8
P002 | 2026-09-14 | Level 2, Room 216 | Drywall | Joint crack at ceiling corner | Finishes | Medium | Drywall foreman | 2026-09-28 | Closed | 2026-09-26 |  |  | 12
P003 | 2026-09-15 | Level 3, Corridor | Electrical | Cover plate missing at outlet | MEP | Medium | Electrical foreman | 2026-09-29 | Closed | 2026-09-27 | I05 |  | 12
P004 | 2026-09-15 | Level 3, Room 305 | Carpentry | Door does not latch | Doors and hardware | High | Carpentry foreman | 2026-09-24 | Ready for recheck |  | I06 |  | 22 | Overdue | 13 | 15-30 days
P005 | 2026-09-16 | Level 3, Room 308 | Flooring | Gap at transition strip | Finishes | Medium | Flooring foreman | 2026-10-02 | In progress |  |  |  | 21 | Overdue | 5 | 15-30 days
P006 | 2026-09-17 | Level 1, Lobby | Cleaning | Construction dust on glazing | Cleaning | Low | General cleaner | 2026-10-05 | Open |  |  |  | 20 | Overdue | 2 | 15-30 days
P007 | 2026-09-17 | Level 1, Mech room | Mechanical | Missing pipe labels | MEP | Medium | Mechanical foreman | 2026-10-01 | Open |  | I02 |  | 20 | Overdue | 6 | 15-30 days
P008 | 2026-09-18 | Level 2, Room 220 | Paint | Uneven finish on feature wall | Finishes | High | Paint foreman | 2026-09-26 | Open |  |  |  | 19 | Overdue | 11 | 15-30 days

## Lists
LISTS & SETTINGS
Single source for every dropdown and the Dashboard. Edit the yellow cells; do not rename column headers. To add a list item, type in the first empty row beneath a list. New categories, trades, priorities and statuses also need a row added on the Dashboard.
Category | Trade | Priority | Status | Point type | ITP status | Min days open | Age bucket | Setting | Value
Finishes | Carpentry | High | Open | Hold | Planned | 0 | 0-7 days | Closed status | Closed
MEP | Cleaning | Medium | In progress | Witness | Scheduled | 8 | 8-14 days | Due-soon window (days) | 7
Doors and hardware | Drywall | Low | Ready for recheck | Review | Passed | 15 | 15-30 days | As-of date override (blank = today)
Cleaning | Electrical |  | Closed |  | Failed | 31 | 31+ days | Effective as-of date | 2026-10-07
Structural | Flooring |  |  |  | N/A
Other | Glazing
Mechanical
Paint
Plumbing
Roofing
General contractor
Other
Settings notes
Closed status: the status that means an item is finished. Dashboard and overdue logic read it.
Due-soon window: items due within this many days (and not overdue) are flagged 'Due soon'.
As-of date override: enter a date to report as at that day; leave blank to use today.
Age buckets: edit the minimum days (ascending, first must be 0); labels update automatically.
Formulas:
Value = IF([Value, row above]="",TODAY(),[Value, row above])