## Start Here
RISK ASSESSMENT REGISTER
Find the hazards, score the risk, choose controls, assign actions, and keep reviews on schedule.
What this workbook does
A register of workplace hazards and risks. Each hazard is scored for severity and likelihood before and after controls, with the hierarchy-of-controls level, an owner, a due date and a review date. The Dashboard shows where the risk sits, how much the controls have reduced it, and what is overdue.
How to use it
Step | What to do | Details | Go to
1 | Set up the scales | Agree the severity and likelihood scales and the band limits with your team. Edit the yellow cells if your site uses different criteria, and add your areas and owners to the lists. | Open Settings >
2 | List and score hazards | For each hazard, enter the area, activity, harm, who is exposed and the controls that exist now. Score severity and likelihood from 1 to 5. The risk score and band calculate. | Open Register >
3 | Choose additional controls | Start with elimination and substitution, then engineering, administrative controls, and PPE last. Pick the control level, then score the residual severity and likelihood. | Open Register >
4 | Assign and track actions | Set an owner, a due date and a status. Enter the date assessed and the review interval in months. The next review date and its status calculate. | Open Register >
5 | Read the dashboard | See risks by band before and after controls, the heat map, the top 10 residual risks, the control mix, and overdue actions and reviews. | Open Dashboard >
Color key
| Input | Yellow cells are inputs. Type or pick a value.
| Calculated | Gray cells contain formulas. Do not overwrite them.
| Overdue | A due date or review date in the past, and the action is not closed.
| Due soon | Due within the alert window set on the Settings sheet.
| On track / closed | Reviews that are current, and actions marked Done or Verified.
Good practice
A risk matrix supports judgment and does not replace it. Assess with the people who do the work, score the worst credible harm, and verify the controls after they are in place.
The example risks come from an illustrative plant. They are placeholders that show how the formulas work: overwrite them with your own.
Important
Educational template. It supports an organization's safety planning and records. It is not legal, regulatory, or professional safety advice and does not replace your organization's safety program, applicable laws and standards, or qualified safety professionals.

## Dashboard
RISK DASHBOARD
Live from the Register ¦ as of 7 Oct 2026 ¦ 8 risks assessed
| RISKS ASSESSED |  | HIGH OR EXTREME: BEFORE |  | HIGH OR EXTREME: AFTER |  | AVERAGE RISK REDUCTION |  | ACTIONS OVERDUE |  | REVIEWS OVERDUE
| 8 |  | 6 |  | 0 |  | 56.94% |  | 1 |  | 1
| across 7 areas |  | 75% of all risks |  | 0% of all risks |  | initial vs. residual score |  | due soon: 1 ¦ open: 5 |  | due soon: 1
| Risks by band | [5 empty] | Before vs. after controls
| Band | Before | After | Change | Before % | After %
| Low | 0 | 3 | 3 | 0% | 37.5%
| Medium | 2 | 5 | 3 | 25% | 62.5%
| High | 6 | 0 | -6 | 75% | 0%
| Extreme | 0 | 0 | 0 | 0% | 0%
| Total | 8 | 8 | 0 | 100% | 100%
Risk heat map
| Show | After controls |  |  | Cells show the number of risks
| Sev \ Lik | 1 | 2 | 3 | 4 | 5
| 5 | 3 | 0 | 0 | 0 | 0
| 4 | 1 | 0 | 0 | 0 | 0
| 3 | 0 | 2 | 0 | 0 | 0
| 2 | 0 | 2 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0
Severity down, likelihood across. Color is the band for each severity x likelihood.
Top 10 residual risks
| ID | Area |  | Activity or hazard |  |  | Residual | Band | Owner |  | Due | Status
1 | R-04 | Assembly |  | Manual lifting of 25 kg parts |  |  | 6 | Medium | EHS manager |  | 2026-08-31 | Verified
2 | R-06 | Cutting |  | Noise above the action level at the saws |  |  | 6 | Medium | EHS manager |  | 2026-12-15 | Open
3 | R-01 | Press line |  | Press closes on the operator's hands |  |  | 5 | Medium | Production supervisor |  | 2026-11-15 | In progress
4 | R-02 | Shipping dock |  | Forklift and pedestrian conflict |  |  | 5 | Medium | Warehouse lead |  | 2026-09-30 | Done
5 | R-03 | Machining |  | Unexpected start-up during maintenance |  |  | 5 | Medium | Maintenance lead |  | 2026-09-15 | Open
6 | R-05 | Parts washing |  | Solvent vapor in the parts washer |  |  | 4 | Low | Facilities lead |  | 2026-10-25 | In progress
7 | R-07 | Parts washing |  | Wet floor at the wash station |  |  | 4 | Low | Facilities lead |  | 2026-10-20 | Done
8 | R-08 | Weld cell |  | Welding fume |  |  | 4 | Low | Maintenance lead |  | 2027-01-31 | Open
9
10
| Controls by hierarchy level | [5 empty] | Risks by area
| Control level |  | Risks | Share | Mix |  | Area |  | Risks | High/Ext. before | High/Ext. after | Avg. reduction
| Elimination |  | 0 | 0% |  |  | Press line |  | 1 | 1 | 0 | 66.67%
| Substitution |  | 1 | 12.5% | ███ |  | Shipping dock |  | 1 | 1 | 0 | 66.67%
| Engineering |  | 6 | 75% | ███████████████ |  | Machining |  | 1 | 1 | 0 | 50%
| Administrative |  | 1 | 12.5% | ███ |  | Assembly |  | 1 | 1 | 0 | 50%
| PPE |  | 0 | 0% |  |  | Parts washing |  | 2 | 0 | 0 | 52.78%
| Total |  | 8 | 100% |  |  | Cutting |  | 1 | 1 | 0 | 50%
| Top three levels (elimination to engineering) |  |  | 87.5% |  |  | Weld cell |  | 1 | 1 | 0 | 66.67%
| Administrative or PPE only |  |  | 12.5%
[7 empty] | Other or blank area |  | 0
Actions and reviews
| Measure |  |  |  |  | Count
| Open actions (status not closed) |  |  |  |  | 5
| Actions overdue |  |  |  |  | 1
| Actions due soon |  |  |  |  | 1
| Reviews overdue |  |  |  |  | 1
| Reviews due soon |  |  |  |  | 1
| Data check: residual score above initial |  |  |  |  | 0
Formulas:
REVIEWS OVERDUE = IFERROR(IF(INDEX(Risks[Due date],MATCH(A29,Risks[Priority rank],0))="","",INDEX(Risks[Due date],MATCH(A29,Risks[Priority rank],0))),"")
After % = SUMPRODUCT((Risks[Due date]<>"")*(Risks[Due date]<TODAY())*(COUNTIFS(Status_List,Risks[Status],Status_Closed,"Yes")=0))
After % = SUMPRODUCT((Risks[Due date]<>"")*(Risks[Due date]>=TODAY())*(Risks[Due date]-TODAY()<=Due_Soon_Days)*(COUNTIFS(Status_List,Risks[Status],Status_Closed,"Yes")=0))

## Register
RISK REGISTER
Score severity and likelihood from 1 (low) to 5 (high). Yellow cells are inputs; gray cells calculate. Example rows are placeholders: overwrite them.
1 IDENTIFY THE HAZARD | [5 empty] | 2 INITIAL RISK |  |  |  | 3 ADDITIONAL CONTROLS |  | 4 RESIDUAL RISK |  |  |  |  | 5 ACTION |  |  | 6 REVIEW
ID | Area | Activity or hazard | Harm that could result | Who is exposed | Existing controls | Severity (1-5) | Likelihood (1-5) | Initial risk | Initial band | Additional controls | Control level | Residual severity | Residual likelihood | Residual risk | Residual band | Risk reduction | Owner | Due date | Status | Date assessed | Review every (months) | Next review | Review status | Priority rank
R-01 | Press line | Press closes on the operator's hands | Crushing injury | Operators | Fixed guarding; operator training; daily pre-start check | 5 | 3 | 15 | High | Light curtain and two-hand control | Engineering | 5 | 1 | 5 | Medium | 66.67% | Production supervisor | 2026-11-15 | In progress | 2026-03-10 | 12 | 2027-03-10 | OK | 3
R-02 | Shipping dock | Forklift and pedestrian conflict | Struck-by injury | Operators, pedestrians, visitors | Painted walkway lines; horns on forklifts; 5 km/h speed limit | 5 | 3 | 15 | High | Physical barriers and a separate pedestrian walkway | Engineering | 5 | 1 | 5 | Medium | 66.67% | Warehouse lead | 2026-09-30 | Done | 2026-04-02 | 12 | 2027-04-02 | OK | 4
R-03 | Machining | Unexpected start-up during maintenance | Crushing or amputation | Maintenance technicians | Lockout/tagout policy exists but is not audited | 5 | 2 | 10 | High | Lockout/tagout procedure and audits | Administrative | 5 | 1 | 5 | Medium | 50% | Maintenance lead | 2026-09-15 | Open | 2025-09-15 | 12 | 2026-09-15 | Overdue | 5
R-04 | Assembly | Manual lifting of 25 kg parts | Back injury | Assembly operators | Manual handling training; team lifts for heavy parts | 3 | 4 | 12 | High | Lift assists and a lifting height standard | Engineering | 3 | 2 | 6 | Medium | 50% | EHS manager | 2026-08-31 | Verified | 2026-05-20 | 12 | 2027-05-20 | OK | 1
R-05 | Parts washing | Solvent vapor in the parts washer | Respiratory irritation | Washer operators | Lid on the washer; general ventilation | 3 | 3 | 9 | Medium | Substitute a low-VOC cleaner; local exhaust | Substitution | 2 | 2 | 4 | Low | 55.56% | Facilities lead | 2026-10-25 | In progress | 2026-06-01 | 6 | 2026-12-01 | OK | 6
R-06 | Cutting | Noise above the action level at the saws | Hearing loss | Saw operators | Hearing protection issued; last noise survey 3 years ago | 3 | 4 | 12 | High | Quieter blades and enclosures; hearing protection | Engineering | 3 | 2 | 6 | Medium | 50% | EHS manager | 2026-12-15 | Open | 2025-10-20 | 12 | 2026-10-20 | Due soon | 2
R-07 | Parts washing | Wet floor at the wash station | Slip and fall injury | All staff | Warning signs; entry mats | 2 | 4 | 8 | Medium | Drainage and non-slip flooring; spill procedure | Engineering | 2 | 2 | 4 | Low | 50% | Facilities lead | 2026-10-20 | Done | 2026-02-12 | 12 | 2027-02-12 | OK | 7
R-08 | Weld cell | Welding fume | Respiratory harm | Welders | General ventilation; respirators on request | 4 | 3 | 12 | High | Fume extraction at the source | Engineering | 4 | 1 | 4 | Low | 66.67% | Maintenance lead | 2027-01-31 | Open | 2026-07-08 | 6 | 2027-01-08 | OK | 8
Formulas:
Next review = IF(OR(Risks[[#This Row],[Date assessed]]="",Risks[[#This Row],[Review every (months)]]=""),"",EDATE(Risks[[#This Row],[Date assessed]],Risks[[#This Row],[Review every (months)]]))
Review status = IF(Risks[[#This Row],[Next review]]="","",IF(Risks[[#This Row],[Next review]]<TODAY(),"Overdue",IF(Risks[[#This Row],[Next review]]-TODAY()<=Due_Soon_Days,"Due soon","OK")))

## Settings
SETTINGS
Scoring scales, risk band limits, alert window and dropdown lists. Yellow cells are inputs; the Register and Dashboard read from here.
1. Severity and likelihood scales
Score | Severity: worst credible harm | Likelihood: how often it could happen
1 | Minor: first aid only | Rare: not expected to happen
2 | Moderate: medical treatment, no lost time | Unlikely: could happen but not expected
3 | Serious: lost time or restricted work | Possible: could happen at some time
4 | Major: permanent injury or illness | Likely: will probably happen
5 | Catastrophic: fatality or multiple serious injuries | Almost certain: expected to happen
2. Risk band limits
Band | Highest score in band | Score range
Low | 4 | 1 to 4
Medium | 9 | 5 to 9
High | 16 | 10 to 16
Extreme | 25 | 17 to 25
Risk = severity x likelihood (1 to 25). Extreme is any score above the High limit. Band names are fixed; change only the yellow limits.
3. Alert window
Due soon (days) | 30 | Actions and reviews due within this many days are flagged as due soon.
4. Lists used by the dropdowns
Control level | What it means (most to least effective)
Elimination | Remove the hazard entirely
Substitution | Replace with something less hazardous
Engineering | Isolate people from the hazard (guards, ventilation, barriers)
Administrative | Change how people work (procedures, training, rotation)
PPE | Protect the person; last resort
Status | Closed?
Open | No | Actions with a closed status are never counted as overdue.
In progress | No
Done | Yes
Verified | Yes
Area | Owner
Press line | Production supervisor
Shipping dock | Warehouse lead
Machining | Maintenance lead
Assembly | EHS manager
Parts washing | Facilities lead
Cutting
Weld cell
Add areas and owners in the next empty yellow cell, up to row 52. The Register dropdowns pick them up.